## Slide 1: PowerPoint 6: Lean construction and heritage and conservation
PowerPoint presentation
5.6 Principles of heritage and conservation
5.7 Lean construction

## Slide 2: Principles of lean construction
Lean construction is a set of principles and tools designed to facilitate planning and control, maximise value and reduce waste throughout a project.
The lean principles can only be applied fully and effectively in construction by focusing on improving the whole process. This means that collaborative working must be at the forefront of values.

## Slide 3: Principles of lean construction
Focus on the customer (client).
Improve efficiency and minimise waste.
Standardise approaches to construction activities.
Manage and improve processes using standardisation; reduce variation.
Focus on delivering best value.
Focus on continuous review and improvement.
Ensure a clean and safe working environment.

## Slide 4: Continuous improvement
Lean construction focuses on striving for continuous improvement and ensuring value for stakeholders. This means reflecting on the success of a project and reviewing areas for improvement. Creating a culture of feedback and collaborative working will help to focus on this. Audits and formal reviews can also be carried out.

## Slide 5: Just in time deliveries (JIT)
Materials and products can be delivered just in time to reduce the need for storage and help to minimise waste. This method reduces the risk of materials been damaged while stored on site. Supply chain integration is important in order to maximise the effectiveness of JIT.
A prime example of JIT is concrete that is ordered and delivered exactly when the site is ready for it to be poured.

## Slide 6: BIM
A key principle of BIM and lean construction is collaborative working. They are thought of as two separate initiatives but share some of the same core values. Lean principles and methods can be supported by adopting BIM. BIM helps to identify design clashes and focuses on reducing waste.

## Slide 7: Management principles
Lean principles focus on value over cost. By adopting a lean approach, contractors focus on standardised activities which add value and continuously focus on improvement. The main driver is always the customer and their experience. By fully understanding the processes involved in the delivery of a project, the management team can focus on getting it right first time to avoid the need for remedial works which may lead to extra costs and potential time delays.

## Slide 8: Lean thinking during construction
Clear communication
Collaborative working practices (links to CDM 2015)
Training and CPD for the workforce
Teamwork
High morale in the workforce to boost productivity
Regular meetings and toolbox talks to ensure that all workers are well informed

## Slide 9: Lean design
Using AR and VR ensures that client requirements are met aesthetically.
Value management focuses on client values.
The use of integrated design involving BIM encourages close cooperation between clients, designers and contractors.
Standardisation and prefabrication of processes and components improves quality, reduces costs and prevents time delays.

## Slide 10: Conservation
Conservation is the process of maintaining and managing change to a heritage building in a way that sustains and enhances its significance.
Preserving historic buildings is a sustainable way of preserving housing stock and retains their character for future generations to enjoy. Preserving heritage buildings can also help to regenerate areas through tourism or other investment.
There are restrictions in place on the types of work which can be carried out and on the materials that can be selected, depending on the significance of the site.
Protection is given to different categories of heritage sites, from the most significant such as World Heritage Sites or Listed Monuments, to Listed Buildings, Registered Parks and Gardens, Registered Battlefields and Conservation Areas.

## Slide 11: Examples of heritage buildings
Many UK towns and cities have conservation areas, such as Berwick-Upon-Tweed’s bridge and ancient walls.
Harrods Village is a Grade II Listed apartment block. It was formerly the London landmark shop’s furniture warehouse.
The city of Bath has been designated a UNESCO World Heritage Site because of its Roman origins and 18th century stone architecture.

## Slide 12: Listed buildings
A building may be listed if it is of special architectural or historic interest and needs to be protected and preserved.
The National Heritage list contains the details of all listed buildings in England.
Grade I – These buildings are of exceptional interest (around 2.5% of listed buildings are Grade I).
Grade II* – These are important buildings of more than special interest (5.8% of listed building are grade II*).
Grade II – These buildings are of special interest (91.7% of listed buildings are in Grade II).

## Slide 13: The Planning Act (Listed Buildings and Conservation Areas) 1990
Listed building consent is required for demolition, alteration or extension works that affect the character of a building with special architectural or historic interest. Consent must be given by the local planning authority. Materials used must be in line with the original design to protect the building’s aesthetics.
The Planning Act (Listed Buildings and Conservation Areas) was introduced to govern the granting of planning permission for building works on listed buildings and conservation areas.
The act introduced special controls for the alteration, extension of and demolition of structures of historic or architectural special interest, as well as conservation areas. Under the act, local planning authorities have obligations to protect heritage buildings and their settings.

## Slide 14
Any questions?