## Slide 1
PowerPoint 10: Project control
17. Project and programme management
17.3 Project planning and control.

## Slide 2: Objectives
By the end of this session learners should be able to:
outline the key project elements that must be subject to control and monitoring by a project controller.

## Slide 3: Project control
Project control refers to the process of data gathering and analysis that can help decision making in projects.
When projects are running, a manager may check on progress or they may appoint someone to do this for them.
In larger organisations, a project controller creates and maintains a project’s budget and schedule, analyses progress and recommends improvements.

## Slide 4: Monitoring meetings
Monitoring meetings are commonly set up at regular intervals to allow the project to be monitored. Project control will analyse:
Time
Cost/budget
Quality

## Slide 5: Time
The main thing that management will want to know is whether the project is on schedule. Will it finish on time? If not, why not?
If there is some flexibility on the timescale, management may allow an extension. If there isn’t room for movement, then more resources may have to be added to the project in order to complete on time.

## Slide 6: Costs and budget
Project control must always keep track of costs against the budget agreed for the project at the initiation phase of the project life cycle.
Has the project exceeded the budget? Overspending on a project can be dangerous as it will affect the final profitability of the project. In a small business, it can also effect the business’s financial security.
If extra costs are unavoidable (eg an increase in the price of raw materials), project control may investigate whether extra funding can be secured. Project control processes will also ask what might be done to reduce ongoing costs.

## Slide 7: Quality
Project control is also responsible for checking whether the product going to have the quality expected.
Any project should have agreed quality standards so output can be measured against them.
Some markets have quality standards enforced by regulation. Food, pharmaceuticals and medical products have very strict standards and any project will be checked against these regularly. Failure to meet the required standards will mean the product cannot be sold.

## Slide 8: Reporting
If, having looked at budget, quality, cost and time, there is something that needs ‘actioning’, a report must tell the stakeholders (eg company management) what can be done to manage the risks to the project.

## Slide 9: Manage by stages
Manage by stages is a term used to describe how a project is planned, monitored and controlled on a stage-by-stage basis. These stages are separated by decision points, also known as control points.
A control point is a moment at which to assess progress to date and look at the next stage of the plan. Previous stages can also be reviewed.
For example, if at the control point it emerges that a department has progressed faster than expected, the schedule can be adjusted accordingly.

## Slide 10: Benefits and drawbacks of managing by stages
        Sets regular points in the project to check on progress.
        PERT chart can help to identify these points.
        Knowledge from previous stages can inform future stages.
          Good point: everyone on the project will know when they are.
          Bad points: control points can take chunks of the management team’s time and are inflexible. Project teams may be less likely to have ad hoc meetings, storing up issues to the next scheduled meeting.

## Slide 11: Manage by exception
At the start of the project, a business may agree tolerances of time, cost, quality, budget or other factors within which the project should sit. For example, there may be a tolerance of 5% for budgeted costs of materials. If costs increase by 2%, this is within the 5% tolerance and the project manager has the authority to approve it.
Manage by exception is a term used to describe escalating an issue which exceeds the tolerance agreed at the start of the project.
Therefore, if the cost of materials were to be 6% higher than the budget, the project manager would send an exception report to the next management level to raise the exception and enable a decision to be taken.

## Slide 12: Benefits and drawbacks of managing by exception
        Senior management only check parts of the project that are unusual (exceptions).
        The project manager does not check everything with the leadership team, ensuring a streamlined process.
        Highlights incidents where the project is not meeting quality, time, cost or other tolerances.
        Good point: can save time and shows trust in the project manager.
        Bad point: something might get missed – relies on good project management.

## Slide 13: Lessons learned
At the end of the project lifecycle, an evaluation stage ensures that lessons are learned from project. The project team meet to analyse what went well, what didn’t, and what could be improved.
Lessons learned allow a business to implement changes to processes or team structures that mean the next project should deliver faster, to a higher quality and with reduced costs.
Initiation
Planning
Implementation
Monitoring
Reporting
Evaluation

## Slide 14
Any questions?
‘T-LEVELS’ is a registered trade mark of the Department for Education. ‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.