## Slide 1: PowerPoint 9: Project management tools and approaches
PowerPoint presentation
6. Project and change management

## Slide 2: Learning objectives
By the end of this session, learners should be able to:
  Discuss the use of project management approaches to define projects.
  Explain the structure of projects including roles and responsibilities, deliverable and timelines.
  Discuss the formats of large and small projects and how they are tracked and reported on.
  Discuss the methods used to measure project indicators.
  Explain the features and benefits of a range of technology-based project management tools.
  Explain the reporting structures of projects and how they can be presented visually.

## Slide 3: Defining projects
    All project management methodologies offer a combination of logical processes to define the projects being considered.
    Project management practices
      Related series of practices.
      Logical step-by-step plans.
      How to develop a project.
      Control the variables.
      Implement the plan.
      Deliver outcomes.
      Complete and terminate.
    Following any project management methodology provides a framework detailing every step to ensure project managers know what to do to deliver and implement the project on time and within budget.

## Slide 4: Project structure
    The structure of a projects refers to the process of how it is organised.
    Project organisation structure
      Arrangements for decision making.
      How the project will be achieved.
      Project methodology model used.
      Planning how it will be actioned.
      Allocate the budget parameters.
      Resources, staff, materials, tools.
      Deliverables and timelines to be agreed.
      Reporting procedures to stakeholders.
    The project organisation structure is created in collaboration with the clients and specialists from relevant departments working with the project manager.

## Slide 5: Project structure – roles and responsibilities
Generally, each project has three areas of responsibility requiring different kinds of skills and expertise.
Areas of responsibility
  Project leadership: overall management.
  Project board: decision makers/define success.
  Project team: specialists implementing the project.
Each methodology will define its own roles and responsibilities and may use different titles, but the areas of responsibility remain broadly the same.

## Slide 6: Project structure – small and large projects (1)
To understand the difference in scale between small and large projects, consider the definitions of UK government infrastructure projects.
UK government infrastructure project categories
  Small projects: less than £100 million.
  Major projects: (big) over £100 million.
  Mega projects: over £1 billion.
  Organisations must define what a small or large project means to them.
  For micro or small business projects up to £100 may be small and up to £1,000 may be large. It is a subjective decision based on the size and revenues of the organisation.

## Slide 7: Project structure – small and large projects (2)
Projects of any scale have several things in common: start and end dates, resource allocation and a set of deliverables, but differences in scale affect complexity.
Small projects | Large projects
Timelines: last for hours/weeks/months/one year | Timelines: months or several years/decades
Deliverables: goals and objectives; tracking and reporting | Deliverables: overall objectives, tracking and reporting
Costs: budget limits, payment schedule/funded by clients | Costs: budget limits, payment schedule – who pays?
Resources: one person, small teams, specialists or multi-skilled, project manager/other duties | Resources: project manager; team leaders; hundreds/thousands of specialists/general operatives

## Slide 8: Project structure – small and large projects (3)
Small projects | Large projects
Project flow: shorter, simpler, easy to manage; single methodology; responsive to change | Project flow: more complex, several methodologies used; formal communications processes
Rigour: reporting to self/line managers; match tasks against deliverables | Rigour: higher levels of accountability, administration, documentation and red tape
Scalability: as a small project succeeds it can always be scaled up | Scalability: difficult to scale down because of resources committed

## Slide 9: Measuring projects – what to measure
The whole point of implementing projects is to make a difference. Measuring the impacts of any differences are key performance indicators (KPIs) in the success of a project.
Project KPIs
  Specific direct impacts: before/after the project.
  £ value achieved significantly higher than £ cost.
  Return on investment: £ cost of project versus £ impact.
  On time: planned milestones versus actual achievements.
  On budget: forecast costs versus actual costs and % drift.
  Stakeholder engagement and their perception of value.

## Slide 10: Measuring projects – how to measure
Accurate measurement of project progress is always challenging but is important to recognise early warning signs if the project is drifting in any way.
Measurement methods
  Completed units: production units; hours; repetitive tasks; known variables.
  Milestones: each step £ budgeted; based on staff time; % of complete process.
  Start/finish: large projects; % allocated to milestones/deliverables and measured.
  Start/finish: small/short project; assigned/paid 50% on start; 50% paid on finish.
  Cost ratio: budget allocated divided by staff hours; % value of project completion.
  Weighted/equivalent units: tasks and subtasks; with different units of measurement.
  Experience/opinion: expert views; subjective; unscientific; not recommended.

## Slide 11: Features and benefits of technology-based tools
GANTT charts are a visual representation of the progress of a project over time.
GANTT chart features
  Set out tasks from start to finish.
  Schedule and assign project tasks.
  Horizontal structure for critical path.
  Actively monitor every step of progress.
  GANTT charts centralise the project plan so everyone knows where the project is at, what to expect and what still needs to be done.
  Source: GANTT Chart created by author

## Slide 12: GANTT charts: advantages and disadvantages
Like every software tool, GANTT charts have their pros and cons. It does take time to understand how to set them up, but the benefits gained can be immensely helpful.
Advantages | Disadvantages
Offer a clear visual representation of project tasks | Can be very time consuming to set up at the beginning
Can support effective time management schedules | Projects with lots of tasks and sub tasks can become complex
Demonstrate resource allocations across the project | Need constant updating to keep information current
Show % completion of each task | Can’t tell number of hours needed by the size of the bar
Help order complex projects into manageable chunks | Not all tasks/resources are available in a single view of chart
Help project managers coordinate with their teams | Not easy to calculate averages or aggregates

## Slide 13: Critical flow analysis
Critical flow analysis is better known as critical path analysis (CPA). It maps out every task needed to complete a project and the sequence of each task.
Critical path analysis
  Identifies all critical and non-critical tasks.
  Sets minimum and maximum time per task.
  Notes which tasks have dependencies.
  Calculates float/slack time and deadline date.
  The CPA process moves a project from chaos to clarity, making it easier to visualise the flow and priorities of all the tasks in the project.

## Slide 14: Critical path analysis
Starts with a list of every task needed to complete the project.
CPA build a house
  START: Planning permission granted.
  Dig trenches for utilities/water mains.
  Dig and pour foundations and base.
  Build walls/install windows/doors.
  Lay pipes and cables to the house.
  Build the roof, tiles, insulate loft.
  Install and connect kitchen/bathroom.
  Snagging jobs to give high-spec finish.
  END: Hand over keys to house owners.
  In reality, this would be a much more complex list of tasks, but it is useful to illustrate a simple CPA network diagram.

## Slide 15: Critical path analysis – network diagram
CPA network diagram: building a house (Activity on Arrow – AOA)
The activities listed are on the arrows which represent the times and task dependencies.
CPA build a house
The diagram would be developed with estimated min/max days for each (added to the circles known as nodes) then the time for completing the project can be calculated.

## Slide 16: Critical path analysis: advantages and disadvantages
CPA can be presented as a network diagram or a GANTT chart showing the sequence of activities in a project.
Advantages | Disadvantages
It sets out critical tasks that depend on each other in a sequence | CPA does not schedule the teams to tasks
It identifies parallel tasks that can run concurrently with each other | Timings of tasks are based on best guest estimates
It identifies non-critical tasks that are important but won’t hold a project up if they hit any issues | The critical path many not be clear in larger, more complex projects
It gives a calculated estimate of minimum and maximum times for the project duration | It does not enable allocation of other resources, eg materials, deliveries
It gives a clear picture of how to manage the project efficiently | It does not show material costs for each task so budgets can not be calculated in this model
It allows team members to clearly see every step in the project | 

## Slide 17: PERT planning (1)
The project evaluation review technique (PERT) is very similar to critical path analysis. The only difference is how the times of tasks are estimated and calculated.
  PERT steps
  Identify tasks and sequences as for CPA.
  Estimate times for each activity:
        Optimistic time (shortest possible).
        Most likely time (highest probability).
        Pessimistic time (longest it may take).
  Project times are usually measured in weeks but could be days or hours. A weighted average formula is applied to the estimated times to help remove bias from estimates, especially the tendency for unrealistically short timescales:
  Expected time = (Optimistic + 4 × Most likely + Pessimistic) / 6

## Slide 18: PERT planning (2)
After the weighted average formula is calculated, the critical path is determined and the total project time can be calculated more accurately.
  PERT – critical path
  ES – Earliest start time.
  EF – Earliest finish time.
  LS – Latest start time.
  LF – Latest finish time.
  ES/EF show the earliest times tasks may be expected to end.
  ES/EF times are worked forwards through the network diagram.
  LS/LF times are the latest points a task can start/end to avoid delaying a project.
  LS/LF are worked backwards through the network diagram.
  Differences between EF and LF of each task are known as the ‘slack’ for that specific activity.

## Slide 19: Flowcharts
A flowchart is a visual document that uses a series of symbols and shapes connected by arrows to represent the direction of workflow in each stage of a project.
How flowcharts work
  Illustrate the sequence of tasks.
  Identify potential workflow issues.
  Discover potential workflow improvements.
  Present lots of information in a single diagram.
  Colour code resources, processes and associated tasks.
  Flowcharts can be done quickly and easily using paper, pens and stencils for the shapes. Or online, which is more easily updated, using flowchart software.

## Slide 20: Flowcharts – symbols
  Different tasks have specific sets of symbols selected according to the type of flowchart being created.
Symbol | Name | Description
 | Process | Action or process step; is common to all process flowcharts and workflow maps
 | Flow line | Showing the direction the processes and tasks are flowing
 | Data | A parallelogram is the data symbol, showing inputs and outputs of the process
 | Document | Shows parts of the process that create or result in a document
 | Multi- documents | Showing when multiple documents are produced or used
 | Manual input | Showing when users will be required to input information manually

## Slide 21: Flowcharts – symbols
  There are several other symbols available; these are the most commonly used ones.
Symbol | Name | Description
 | Stored data | A step in the process that shows where data are stored rather than actioned
 | Database | The database symbol is instantly recognised and used in other digital management tools
 | Hard drive | Showing when data are stored on an internal or external hard drive
 | Memory storage | Showing when information is stored in memory rather than an external drive or as a file
 | Decision | Used to show when a yes/no decision is needed to create a branch in the flowchart
 | Connector | Small circles are used to show a jump from one point to another in a process and are labelled with capital letters A, B, AA, AB, etc
 | Terminal points | An oval showing start/stop points in a process

## Slide 22: Flowchart – Excel example
Flowcharts can be made in Word, Excel or specifically designed software. This simple example shows a colour-coded sales process.
Flowcharts
  Decisions in red diamond.
  Flow direction arrows in red.
  Documents (email) in purple.
  Processes in blue rectangles.
  Start/stop points in green ovals.
  This flowchart was created using an Excel spreadsheet.

## Slide 23: Pareto analysis (1)
Pareto principle: Analyses problems and causes in different business scenarios, using variables of time, cost, value and frequency of occurrences.
Findings show that 80% of results come from 20% of the causes.
  Pareto results (examples)
  80% of sales revenues from 20% of existing customers.
  80% of customer complaints come from 20% of products.
  80% of production problems caused by 20% of the defects.
  Pareto analysis is a useful tool to help decide the best course of action when many options are available. It estimates the benefits of each option to maximise choices.

## Slide 24: Pareto analysis (2)
Maximising choices: For example, if 80% of sales revenues comes from 20% of customers, who are the ones most of the marketing budget should be aimed at?
  Pareto results – sales campaign
  The majority of buyers were customers who had bought previously, and a substantial number came via social media fans. Email and social media marketing campaigns are likely to have the best return on marketing spend.

## Slide 25: Pareto analysis (3)
  Pareto is a relationship between two quantities. A change in the quantity of one variable will result in a relative proportional change in the other quantity. This deceptively simple process brings some natural pros and cons to using Pareto:
Advantages | Disadvantages
Helps identify main causes/effects/options | Categories of causes and impacts have to be analysed and counted first
Ranks options in order of highest to lowest priority or impact | Does not show depth of impacts or issues
Can identify cumulative effects over long periods of time | Focus is on past data only, no way of accounting for future changes
Improves planning, analysing and decision making of options available and resolving problems | May be prone to human error: counts, scores, categorising impacts

## Slide 26: Plan on a page (POAP)
POAP is defined as a concise visual depiction of key elements of the required strategic impacts of a business or project used by every key player in the project.
Project plan |  |  | 
Step 1: Current state of play: What needs to change/reasons for project or changes |  | Step 2: Where it needs to be: What is desired outcome if the business/project is totally successful. Why is this important | 
Objectives | Strategies |  | Key actions
Step 3: BIG goals: what the business/project impacts will be. Challenging and SMART objectives | Step 4: Strategies to achieve objectives in first column. Who would be brought in to contribute to its success? What model, approaches, tools would be used/bought in? |  | Step 5: Top line actions (not fully detailed action plan yet)
Step 6: Publish completed plan. Distribute to all involved | Step 7: Schedule key actions in everyone’s diary |  | Step 8: Monthly public review of plan done/not/done better/to be changed

## Slide 27: Project initiation documents
Before a project starts, it is important to set clear expectations and boundaries agreed by all stakeholders using a project initiation document (PID).
Steps in creating a PID
Context: strategic vision; purpose; goals.
Parameters: budgets; timelines, communications.
Define specifics: scope; boundaries; deliverables.
Roles and responsibilities: decision makers/operators.
Organisation structure: tasks; hours; budgets; deadlines.
Risks and assumptions: timing, resources, technology, talent.
Share PID for client approval/sign off: then with project teams.
    The PID will be referred to in order to check the project stays within scope or in the event of any queries between internal and external stakeholders.

## Slide 28: Dashboard reports
Dashboard reports gives visual progress checks on project metrics to aid decision making.
Four types of dashboard
Strategic: tracks KPIs; success factors; aids predictions.
Analytical: shows results and trends in graphs, charts, forecasts.
Tactical: tracks progress, explores data, digital interaction, makes changes.
Operational: snapshots, happening now, flags issues; immediate attention.

## Slide 29: Summary – what we did
  Discussed the use of project management approaches to define projects.
  Explained the structure of projects, including roles and responsibilities, deliverable and timelines.
  Discussed the formats of large and small projects and how these are tracked and reported on.
  Discussed the methods used to measure project indicators.
  Explained the features and benefits of a range of technology-based project management tools.
  Explained the reporting structures of projects and how they can be presented visually.

## Slide 30
Any questions?
‘T-LEVELS’ is a registered trade mark of the Department for Education. ‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.